## PERT
PERT (Program and Evaluation Review Technique)
No. | Task | Assignment | Result | Dependent | o (Optimistic Time) | r (Realistic Time) | p (Pessimistic Time) | ET (Expected Time)
1 | Topic analysis, market survey, topic selection and introducing topics | All | Requirement Documents |  | 1 | 2 | 3 | 2
2 | Business analysis |  | Information of fashion market |  | 4 | 7 | 10 | 7
2.1 | Targets, areas and products | An Bình |  | 1 | 1 | 2 | 3 | 2
2.2 | Market analysis | Phương Oanh |  | 1 | 1 | 2 | 3 | 2
2.3 | Analyze competitive environment and competitive advantage | An Bình |  | 1 | 2 | 3 | 4 | 3
3 | Analysis business models |  | Business model |  | 6 | 9 | 12 | 9
3.1 | Customer segments Key Activities Customer Relationships Key Resources | Phương Oanh |  | 1,2 | 2 | 3 | 4 | 3
3.2 | Value proposition Key Partnerships Key Activities | An Bình |  | 1,2 | 2 | 3 | 4 | 3
3.3 | Revenue Streams Cost Structure | Huyền Trang |  | 1,2 | 2 | 3 | 4 | 3
4 | Design Website, fanpage on social media |  | Website system and fanpages |  | 7 | 11 | 15 | 11
4.1 | Describe about format | Huyền Trang | A format website | 2,3 | 2 | 3 | 4 | 3
4.2 | Design detailed | Huyền Trang | A complete website | 4.1 | 4 | 6 | 8 | 6
4.3 | Create fanpage | Phương Oanh An Bình | Fanpages | 2,3 | 1 | 2 | 3 | 2
5 | Project Evaluation Process | All | Word, Excel, Power point,.. | 3,4 | 2 | 3 | 4 | 3

## AOA_AON
AOA&AON
1. AOA (Activity On Arrow) | 2. AON (Activity On Node)

## GANTT
GANTT CHART_Version 1
Project start date: |  | 2020-10-26
Display week: |  | 0
Deadline: |  | 2020-12-02 |  |  |  | 2020-10-27 | [6 empty] | 2020-11-03 | [6 empty] | 2020-11-10 | [6 empty] | 2020-11-17 | [6 empty] | 2020-11-24 | [6 empty] | 2020-12-01
 | time axis 2020-10-25 to 2020-12-07
Task | Start | End | Duration | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
1 | 2020-10-26 | 2020-10-28 | 2
2 | 2020-10-28 | 2020-11-04 | 7
3 | 2020-11-03 | 2020-11-12 | 9
4 | 2020-11-10 | 2020-11-21 | 11
5 | 2020-11-21 | 2020-11-24 | 3
Changelog
1 | Change | Change the start time of Task 2 form 28-Oct to 1-Nov
2 | Change | Task 4 is finishsed at 15-Nov Duration is lated 2 days (from 5 days to 7 days)
3 | Check | The group performs the report review and submits
4 | Present | The group prepared for the presentation on 2-Dec
GANTT CHART_Version 2
Project start date: |  | 2020-10-26
Display week: |  | 0
Deadline: |  | 2020-12-02 |  | 2020-10-27: 2020-10-27; 2020-11-03: 2020-11-03; 2020-11-10: 2020-11-10; 2020-11-17: 2020-11-17; 2020-11-24: 2020-11-24; 2020-12-01: 2020-12-01
 | time axis 2020-10-25 to 2020-12-07
Task | Start | End | Duration | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
1 | 2020-10-26 | 2020-10-28 | 2
2 | 2020-10-30 | 2020-11-08 | 9
3 | 2020-11-08 | 2020-11-15 | 7
4 | 2020-11-15 | 2020-11-26 | 11
5 | 2020-11-25 | 2020-11-28 | 3